## Sheet1
Task | Time Required (days) | Status | Comment
Master Page | 0.5 | Completed
Login Page | 0.5 | 90% done | minor code behind pending
Registration Page | 0.5 | In Progress
Home Page | 2 | Not Started
Dog Food Page | 2 | Not Started
Dog Products Page | 2 | Not Started
Adoption Page | 3 | Not Started
About Us Page | 0.5 | Not Started
Cart Page | 3 | Not Started